## Verification
ID | Requirement | Source | Category (Requirement/ Observation) | P&ID | Phase Name | Implementation (PLC/HMI) | Verification Method (Test/Review) | Tracking Ticket | Ticket Status | Closeout Comment | FAT Signoff | SAT Signoff
POB-001 | Project Objectives Fully automate transport system purge during plant shutdown | Email Ravi 20/07/2026 | Observation
POB-002 | Prevent packer empty-out sequences from commencing until transport purge is complete | Email Ravi 20/07/2026 | Observation
POB-003 | Automate packer empty-out processes currently requiring manual intervention | Email Ravi 20/07/2026 | Observation
POB-004 | Improve powder recovery from storage bins and vacuum conveying systems | Email Ravi 20/07/2026 | Observation
POB-005 | Minimize residual powder remaining in bins, transport lines, and vacuum cans | Email Ravi 20/07/2026 | Observation
POB-006 | Provide configurable operating parameters where appropriate | Email Ravi 20/07/2026 | Requirement |  |  | PLC, HMI | Review | FWH1062-7 | In Progress
SOW-TSS-001 | 1. Transport System Shutdown Purge Sequence: Existing Issues - An automated transport line purge exists but activation logic requires verification. - Current shutdown behaviour may not completely empty transport lines or alternate destination bins. - Selection PwdPRWP12 – Drain Tipping Transport Line exists but contains no implemented PLC logic. | Email Ravi 20/07/2026 | Observation | 556-17 | PwdPRWP11 - Tipping Transport to Silos PwdPRWP12 - Drain Tipping Transport Line |  | Review | FWH1062-1 | Discuss
SOW-TSS-002 | Allow normal transport operation until: - Sifter shutdown complete. - Fluid bed shutdown complete. | Email Ravi 20/07/2026 | Requirement | 556-05 | PwdSxP01 - Tipping to Powder Silo x PwdSxP03 - P3 to Powder Silo x PwdSxP04 - P4 to Powder Silo x PwdSxP05 - P5 to Powder Silo x | PLC, HMI | Test | FWH1062-2 | Discuss
SOW-TSS-003 | Initiate transport line purge: - Purge initially to the currently selected destination bin. - Automatically switch and purge to the alternate bin. | Email Ravi 20/07/2026 | Requirement | N/A | TBC | PLC, HMI | Test | FWH1062-3 | Discuss
SOW-TSS-004 | Upon completion of transport purge: - Trigger one additional vacuum can cycle. - Verify all low-level and high-level powder conditions are cleared. - Return system to standby/shutdown state. | Email Ravi 20/07/2026 | Requirement | 556-17 | PwdPRWP11 - Tipping Transport to Silos | PLC, HMI | Test | FWH1062-4 | Discuss
SOW-TSS-005 | Interlocking Implement interlock preventing packer empty-out sequence from starting until Transport purge sequence has completed successfully. | Email Ravi 20/07/2026 | Requirement | 556-06, 556-07, 556-14 | PwdSxE01 - Powder Silo x | PLC, HMI | Test | FWH1062-5 | Discuss
SOW-TSS-006 | Investigation Required to Determine purpose and intended functionality of PwdPRWP12 – Drain Tipping Transport Line | Email Ravi 20/07/2026 | Observation | 556-17 | PwdPRWP11 - Tipping Transport to Silos PwdPRWP12 - Drain Tipping Transport Line |  | Review | FWH1062-1 | Discuss
SOW-TSS-007 | Deliverables - Updated PLC shutdown sequence. - Updated HMI status indications. - Verification testing during shutdown operation. | Email Ravi 20/07/2026 | Requirement | N/A | N/A | PLC, HMI | Test | FWH1062-6 | Discuss HMI status indicators
SOW-PEA-001 | 2. Packing Empty-Out Automation Existing Situation Current empty-out process requires operator intervention. Investigation Required Document and review: - Current operator actions. - Existing SOPs. - Manual steps performed by packing operators. | Email Ravi 20/07/2026 | Observation | TBC | TBC |  | Review | FWH1062-8 | Discuss which machine(s) this applies to.
SOW-PEA-002 | Develop automated PLC sequence to: - Replicate current operator empty-out procedure. - Minimize manual intervention. - Ensure consistent packer emptying process. | Email Ravi 20/07/2026 | Requirement |  |  | PLC, HMI | Test
SOW-PEA-003 | Deliverables - Functional design update. - PLC sequence development. - Operational testing and validation. | Email Ravi 20/07/2026 | Requirement |  |  | PLC, HMI | Test
SOW-BTP-001 | 3. Bin-to-Packer Empty-Out Improvements Existing Issues Current empty-out sequence performs adequately but: Bins 1 and 3 feeding A Packer retain approximately: - 50 kg to 100 kg of powder. Issue caused by: - Pipe arrangement. - Shape of new bustle design. | Email Ravi 20/07/2026 | Observation | 556-06, 556-07, 556-14 | PwdSxP27 - Powder Silo x to Bulk Packer Primary PwdSxP28 - Powder Silo x to Bulk Packer Secondary | PLC, HMI | Review | FWH1062-9 | Discuss hardware mods
SOW-BTP-002 | Potential Hardware Modification Investigate installation of bin vibrators on: Powder Silo 1 to Bulk Packer - PwdS1P27 - PwdS1P28 Powder Silo 3 to Bulk Packer - PwdS3P27 - PwdS3P28 | Email Ravi 20/07/2026 | Observation | 556-06, 556-07, 556-14 | PwdSxP27 - Powder Silo x to Bulk Packer Primary PwdSxP28 - Powder Silo x to Bulk Packer Secondary | PLC, HMI | Review
SOW-BTP-003 | PLC Modifications If vibrators are installed: - Enable automatically during transfer steps. - Disable once transfer/empty-out sequence completes. - Include alarm and permissive handling. | Email Ravi 20/07/2026 | Observation | 556-06, 556-07, 556-14 | PwdSxP27 - Powder Silo x to Bulk Packer Primary PwdSxP28 - Powder Silo x to Bulk Packer Secondary | PLC, HMI | Review
SOW-BTP-004 | Additional Requirement Empty-out sequence must automatically empty: - Both bins aligned to plant operation. Currently this activity is performed manually by operators. | Email Ravi 20/07/2026 | Requirement | 556-09, 556-13 | PwdBlkxP01 - Transport to Bulk Packer x PwdBlkxP21 - Bulk Packer x Weigh Hopper | PLC, HMI | Test | FWH1062-10 | Discuss
SOW-BTP-005 | Investigation Required Obtain: - Existing operator procedure. - Detailed empty-out methodology. - SOP documentation. | Email Ravi 20/07/2026 | Observation | 556-09, 556-13 | PwdBlkxP01 - Transport to Bulk Packer x PwdBlkxP21 - Bulk Packer x Weigh Hopper |  | Review | FWH1062-10 | Discuss
SOW-BTP-006 | Deliverables - PLC modifications. - Vibrator control integration (if approved). - Functional testing. | Email Ravi 20/07/2026 | Requirement | 556-06, 556-07, 556-14, 556-09, 556-13 | PwdSxP27 - Powder Silo x to Bulk Packer Primary PwdSxP28 - Powder Silo x to Bulk Packer Secondary PwdBlkxP01 - Transport to Bulk Packer x PwdBlkxP21 - Bulk Packer x Weigh Hopper | PLC, HMI | Test | FWH1062-9, FWH1062-10 | Discuss
SOW-PTE-001 | 4. Purge Time Enhancement Requirement Review and modify purge timing strategy to: - Extend purge duration where required. - Allow configurable purge time override/setpoint. Deliverables - Configurable PLC parameters. - HMI operator settings page. - Documentation update. | Email Ravi 20/07/2026 | Requirement | N/A | N/A | HMI | Test | FWH1062-11 | Discuss HMI options
SOW-VEA-001 | 5. Vacuum Can Empty-Out Automation Existing Situation Operators manually empty the four vacuum cans after bin empty-out timer completion. Proposed Automation Automate final can emptying process by: - Executing two additional vacuum conveying cycles after bin empty-out timer completes. PLC Logic Modification Repeat the following sequence steps: - Step 16 - Step 18 - Step 20 for configurable repeat cycles. | Email Ravi 20/07/2026 | Requirement | 556-09 | PwdBlkAP11 - Bulk Packer A Vacuum Can 1 PwdBlkAP12 - Bulk Packer A Vacuum Can 2 PwdBlkAP13 - Bulk Packer A Vacuum Can 3 PwdBlkAP14 - Bulk Packer A Vacuum Can 4 | PLC, HMI | Test | FWH1062-12 | Discuss
SOW-VEA-002 | Recommended Enhancement Create adjustable parameter: Additional Empty-Out Cycles - Default = 2 cycles - Adjustable by authorized personnel | Email Ravi 20/07/2026 | Requirement | 556-09 | PwdBlkAP11 - Bulk Packer A Vacuum Can 1 PwdBlkAP12 - Bulk Packer A Vacuum Can 2 PwdBlkAP13 - Bulk Packer A Vacuum Can 3 PwdBlkAP14 - Bulk Packer A Vacuum Can 4 | PLC, HMI | Test | FWH1062-12 | Discuss
SOW-VEA-003 | Deliverables - PLC logic enhancement. - Operator-adjustable cycle parameter. - Testing and commissioning. | Email Ravi 20/07/2026 | Requirement | 556-09 | PwdBlkAP11 - Bulk Packer A Vacuum Can 1 PwdBlkAP12 - Bulk Packer A Vacuum Can 2 PwdBlkAP13 - Bulk Packer A Vacuum Can 3 PwdBlkAP14 - Bulk Packer A Vacuum Can 4 | PLC, HMI | Test | FWH1062-12 | Discuss
EXC-001 | Exclusions The following items are excluded unless separately approved: - Mechanical installation of vibrators. | Email Ravi 20/07/2026 | Exclusion
EXC-002 | - Structural modifications to silos, bins, pipework or bustles. | Email Ravi 20/07/2026 | Exclusion
EXC-003 | - Replacement of conveying equipment. | Email Ravi 20/07/2026 | Exclusion
EXC-004 | - Major redesign of transport routing. | Email Ravi 20/07/2026 | Exclusion
EXC-005 | - Third-party OEM software modifications outside PLC control scope. | Email Ravi 20/07/2026 | Exclusion
ASS-001 | Assumptions 1. Existing PLC hardware has sufficient capacity for logic additions. | Email Ravi 20/07/2026 | Assumption
ASS-002 | 2. Existing HMI system can accommodate required screens and parameters. | Email Ravi 20/07/2026 | Assumption
ASS-003 | 3. Current functional descriptions and PLC code accurately reflect plant operation. | Email Ravi 20/07/2026 | Assumption
ASS-004 | 4. Operations personnel will provide SOPs describing current manual processes. | Email Ravi 20/07/2026 | Assumption
ASS-005 | 5. Access to Tetra Pak/Macro support will be available if required. | Email Ravi 20/07/2026 | Assumption
RSK-001 | Key Risks Risk / Impact Existing process knowledge incomplete / Additional engineering effort | Email Ravi 20/07/2026 | Risk
RSK-002 | Lack of documented manual procedures / Delays to automation design | Email Ravi 20/07/2026 | Risk
RSK-003 | Residual powder caused by mechanical design limitations / May require hardware solutions | Email Ravi 20/07/2026 | Risk
RSK-004 | Undefined PwdPRWP12 functionality / Potential scope growth | Email Ravi 20/07/2026 | Risk
RSK-005 | Production testing availability / Commissioning delays | Email Ravi 20/07/2026 | Risk
CRI-001 | Success Criteria - Transport lines fully purged during plant shutdown. | Email Ravi 20/07/2026 | Criteria
CRI-002 | - Packer empty-out interlocked with transport purge completion. | Email Ravi 20/07/2026 | Criteria
CRI-003 | - Reduction in manual operator intervention. | Email Ravi 20/07/2026 | Criteria
CRI-004 | - Automated emptying of vacuum cans. | Email Ravi 20/07/2026 | Criteria
CRI-005 | - Reduced powder hold-up in bins and conveying systems. | Email Ravi 20/07/2026 | Criteria
CRI-006 | - Configurable purge and empty-out parameters available through HMI. | Email Ravi 20/07/2026 | Criteria
CRI-007 | - Successful commissioning and operator sign-off. | Email Ravi 20/07/2026 | Criteria